## About (hidden)
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks description, select a category of Goal, Milestone, On Track, Low Risk, Med Risk, High Risk, Progress as a percent of task completion, a Start Date and Number of days to complete the task. The Gantt chart fills in and is color coded to help distinguish the various categories. A scroll bar allows you to scroll through the timeline. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. Gantt Chart About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
This is the last instruction in this worksheet.

## Gantt
Create a Gantt Chart in this worksheet. Enter title of this project in cell B1. Legend title is in cell I1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | Theme 3: Enhance the Student Experience - YEAR 1 | [8 empty] | Legend:
Enter Company Name in cell B2. A legend is in cells I2 through AC2. | Executive Co-Sponsors: Al Thompson and Marty Loy | [8 empty] | Goal |  |  |  |  | Outcome |  |  |  |  | Strategy |  |  |  |  | Metric
pw:UWSPstratplan
Implementation Co-Chairs: Joshua Hagen and Laura Ketchum-Ciftci
Implementation Team: Lindsay Bernhagen, Kyle Beyersdorf, Will Scheder, Gretel Stock
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell F3 or allow the sample formula to find the smallest date value from the Gantt Data table. Project Start Date: label is in cell D3. |  |  |  |  | Project Start Date: |  | 2021-07-01 |  |  | YEAR 1 | [11 empty] | YEAR 2 | [11 empty] | YEAR 3 | [11 empty] | YEAR 4 | [11 empty] | YEAR 5
A Scrolling Increment is in cell F4. Months for the dates in row 5 are displayed starting in cells I4 through cell BL4. Do not modify these cells. They are auto updated based on the project start date in cell F3. | [9 empty] | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Cells I5 through BL5 contain the day number of the month for the Month represented in the cell block above each date cell and are auto calculated. Do not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2021-07-01 to 2026-06-01
This row contains headers for the project schedule that follows below them. Navigate from B7 through BL7 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I7 and continues through cell BL7. All project timeline charting is auto generated based on the category, start date and number of days entered in the Milestones table. | Milestone Description | Purpose Made Possible Goal | Responsible Division | Category | Assigned To | Progress | Start | No. Days | Resource Needs | time axis 2021-07-01 to 2026-06-01
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Enter Project information starting in cell B9 through cell G9. Sample data is in cells B9 through G33. Enter Milestone Description, select a Category from the drop-down list, assign someone to the item, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. | We will prioritize and expand high-impact practices (HIP) to boost student learning, development, and engagement. | Student Experience 1.1 |  | Goal
| Focus efforts on equitable student access to HIPs we can do well as an institution and for which we can demonstrate markers of quality, ensuring that all students participate in at least two HIPs during their college career, with at least one taking place during their first year on campus. | Student Experience 1.1 |  | Outcome |  |  | 2021-07-01 | 1825
| Develop a shared understanding of markers of quality and a rubric for assessing existing and new high impact practices. | Student Experience 1.1 | Academic Affairs / Student Affairs | Strategy | SAAT Chair & CITL |  | 2022-01-01 | 547 | Faculty Stipend ($15K)
| Rubric adopted by Dec 2022 for implementation in spring 2023 | Student Experience 1.1 | Academic Affairs / Student Affairs | Metric | SAAT Chair & CITL |  |  |  | Faculty Stipend ($15K)
| Ensure that every graduate can demonstrate mastery of rigorous critical thinking skills utilizing assessments familiar to employers. | Student Experience 1.1 | Academic Affairs | Strategy | Director, Critical Thinking Center | In Progress | 2021-07-01 | 1825 | Cost for student instrument ($7/student or ca. $40,000)
| Assessment results for first-year vs. graduating students | Student Experience 1.1 | Academic Affairs | Metric | Director, Critical Thinking Center |  | 2022-09-01
| Increase internships/capstone placements across all Student Affairs departments – childcare, graphic design and marketing, residential living, culinary arts, etc. | Student Experience 1.1 | Student Affairs | Strategy | VCSA/SA Departmental Directors |  | 2022-01-01 | 365 | Staff Time
| Number of students participating in internships/capstsone placements in Student Affairs departments | Student Experience 1.1 | Student Affairs | Metric | VCSA/SA Departmental Directors |  |  |  | Staff Time
| We will deliver vibrant yet tailored student services that support the retention and success of all students. | Student Experience 1.2 |  | Goal
| Achieve and maintain a minimum annual first-to-second year retention rate of 80%. | Student Experience 1.2 |  | Outcome |  |  | 2021-07-01 | 1825
| Identify high DFW courses with departments and recommend changes. | Student Experience 1.2 | Academic Affairs | Strategy | Retention Steering Committee |  | 2022-01-01 | 547 | Staff Time
| List of courses and recommendations submitted to academic units by Dec 2022 | Student Experience 1.2 | Academic Affairs | Metric | Retention Steering Committee |  |  |  | Staff Time
| Partner with degree-granting colleges, programs, and constituent groups to develop retention targets for programs and student segments. | Student Experience 1.2 | Academic Affairs | Strategy | ORIE/ University College |  | 2021-10-01 | 365
| Retention targets communicated to programs by spring 2022 | Student Experience 1.2 | Academic Affairs | Metric | ORIE/ University College
| Work with Navigate teams and other tools to integrate and communicate support for first-year students intentionally and strategically in the curriculum, co-curriculum, student support, and financial operations. | Student Experience 1.2 | Academic Affairs | Strategy | Director, Student Retention |  | 2022-03-01 | 730 | Staff Time
| Creation and use of a tracking mechanism to manage student communication across units | Student Experience 1.2 | Academic Affairs | Metric | Director, Student Retention |  |  |  | Staff Time
| Investigate and suggest strategies to address the root causes of attrition to the technical colleges in the first year. | Student Experience 1.2 | Academic Affairs | Strategy | Retention Steering Committee |  | 2022-01-01 | 365 | Staff Time
| Submit strategies to Academic Affairs and Student Affairs by December 2021 | Student Experience 1.2 | Academic Affairs | Metric | Retention Steering Committee
| Identify and scale up successful retention initiatives within Student Affairs. Improve coordination, collaboration, and communication around retention and student success. | Student Experience 1.2 | Student Affairs | Strategy | VCSA/SA Departmental Directors |  | 2022-01-01 | 730 | Future financial commitment
| Initiatives are identified and revised by summer 2022 for implementation in fall 2022 | Student Experience 1.2 | Student Affairs | Metric | VCSA/SA Departmental Directors
| Ensure that all incoming students can receive a full-year academic schedule during STAR by May 2022. | Student Experience 1.2 |  | Outcome |  |  | 2021-07-01
This row marks the end of the Gantt milestone data. DO NOT enter anything in this row. To add more items, insert new rows above this one. | Implement use of the Navigate or Peoplesoft academic planning tools to allow students to graduate on time with the help of a four-year plan developed in tandem with an academic advisor during their first semester on campus by May 2022. | Student Experience 1.2 | Academic Affairs | Strategy | University College / Academic Advising & Registrar |  | 2021-10-01 | 365 | Up to $75,000 annually for planning tool
| Successful deployment and utilization of academic planning tools by departments and schools | Student Experience 1.2 | Academic Affairs | Metric | University College / Academic Advising & Registrar |  |  |  | Staff Time
| Develop an intentional plan to increase student engagement to foster a “Sense of Belonging” for all UWSP Students | Student Experience 1.2 |  | Outcome
| Grow SPIN usage by Student Affairs departments and UWSP students by 15% to cultivate increased student engagement. | Student Experience 1.2 | Student Affairs | Strategy | University Centers/ CASE | Begun | 2021-07-01 | 365 | Staff Time
| 15% Increase in usage of SPIN 15% by May 2022 to better understand student engagement and which students appear not to be engaged | Student Experience 1.2 | Student Affairs | Metric | University Centers/ CASE | Begun |  |  | Staff Time
| Enhance student service support to the branch campuses | Student Experience 1.2 | Student Affairs | Strategy | VCSA / SA Departmental Directors |  | 2022-01-01 | 365 | Staff Time and Money
| Identify specific support services for enhancement by May 2022 and implement in fall 2022 | Student Experience 1.2 | Student Affairs | Metric | VCSA / SA Departmental Directors |  |  |  | Staff Time and Money
| We will build and enhance a community that values inclusion, equity, and diversity. | Student Experience 1.3 |  | Goal
| Achieve a 10% increase in first-to-second year retention of students of color by 2025. | Student Experience 1.3 |  | Outcome |  |  | 2021-07-01 | 1825
| Create a team of faculty, staff and students who are experts in their areas to draft a plan on addressing closing the institutional achievement gap. | Student Experience 1.3 | Academic Affairs / Student Affairs | Strategy | Provost/VCSA |  | 2022-01-01 | 365 | Staff Time
| Team created by spring 2022 and plan completed by Dec 2022 | Student Experience 1.3 | Academic Affairs / Student Affairs | Metric | Provost/VCSA |  |  |  | Staff Time
| Identify through exit interviews, case-load model student-advisor engagement, and other tactics the reasons why students of color leave and stay at UWSP. | Student Experience 1.3 | Academic Affairs / Student Affairs | Strategy | Provost/VCSA |  | 2022-01-01 | 365 | Salary for grad student to collect data
| List of reasons submitted to Academic Affairs and Student Affairs by May 2022 | Student Experience 1.3 | Academic Affairs / Student Affairs | Metric | Provost/VCSA
| Ensure that UWSP provides opportunities for high quality engagement with social justice content to all students, faculty, staff, and community members by fall 2023. | Student Experience 1.3 |  | Outcome |  |  | 2021-07-01 | 730
| Gather baseline data as to where and how in the major/minor curriculum and programming students are encountering social justice and EDI issues. | Student Experience 1.3 | Academic Affairs | Strategy | University College/CITL Director | Done | 2021-07-01 | 365 | Staff Time
| Data collection complete by December 2021 | Student Experience 1.3 | Academic Affairs | Metric | University College/CITL Director | Done |  |  | Staff Time
| Develop a social justice institute that examines the root cause of social injustice and helps to develop innovative solutions. | Student Experience 1.3 | Academic Affairs / Student Affairs | Strategy | VCSA/CDO & CITL Director | Done | 2021-07-01 | 730 | $100,000 for institute
| Proposal completed by May 2022 for review and implementation during 2022-2023 | Student Experience 1.3 | Academic Affairs / Student Affairs | Metric | VCSA/CDO & CITL Director | Proposal completed, Implementation being working on
| Collaborate with Academic Affairs (CITL) to provide enhanced student inclusivity and cultural competency trainings. | Student Experience 1.3 | Academic Affairs / Student Affairs | Strategy | VCSA/CDO & CITL Director | Begun | 2021-07-01 | 730 | $30,000 CITL faculty fellows
| Enhanced training program developed by May 2022 for implementation starting in fall 2022 | Student Experience 1.3 | Academic Affairs / Student Affairs | Metric | VCSA/CDO & CITL Director
| Evaluate and reward contributions to EDI work by faculty and academic staff by fall 2023. | Student Experience 1.3 |  | Outcome |  |  | 2021-07-01 | 730
| Require annual EDI reporting relevant to the goals listed in the Academic Affairs EDI Strategic Plan from all schools and/or colleges. | Student Experience 1.3 | Academic Affairs | Strategy | Academic Affairs/CITL | In Progress | 2021-07-01 | 365
| Reporting template and timeline communicated to schools and/or colleges by spring 2022 | Student Experience 1.3 | Academic Affairs | Metric | Academic Affairs/CITL
| Refine policies for addressing incidents of hate and bias from faculty and staff toward students and their colleagues so that offending parties are held accountable and supported in efforts toward change in a consistent manner. | Student Experience 1.3 | Academic Affairs / Student Affairs | Strategy | DCA Director | In Progress | 2021-07-01 | 365 | Staff tIme /internal trainings/ $2,500
| Policy revisions proposed by spring 2022 for implementation in fall 2022 | Student Experience 1.3 | Academic Affairs / Student Affairs | Metric | DCA Director |  |  |  | Staff tIme /internal trainings/ $2,500
| Add department, faculty and staff metrics for contributions to EDI work to UWSP’s annual recognition process. | Student Experience 1.3 | Academic Affairs/ CDO | Strategy | University Awards Committee | In Progress | 2021-07-01 | 365
| New rubrics announced and in place for fall 2022 | Student Experience 1.3 | Academic Affairs/ CDO | Metric | University Awards Committee
| Make contributions toward EDI a mandatory metric for all annual personnel (P&T, merit, etc.) and program reviews, and hold people accountable when no progress is made. | Student Experience 1.3 | Business Affairs/Academic Affairs | Strategy | Human Resources | In Progress | 2021-07-01 | 730 | Staff Time
| Revise review process by December 2021 for implementation in 2022 | Student Experience 1.3 | Business Affairs/Academic Affairs | Metric | Human Resources |  |  |  | Staff Time
| Improve recruitment and retention of underrepresented faculty and academic staff. | Student Experience 1.3 |  | Outcome |  |  | 2021-07-01 | 1825
| Revise the role and mechanisms of course evaluations in order to minimize the effects implicit bias, explicit racism, homophobia, transphobia, sexism, ableism, xenophobia, etc. from students. | Student Experience 1.3 | Academic Affairs | Strategy | Academic Affairs / CITL |  | 2021-07-01 | 730
| Changes proposed by December 2021 for implementation in fall 2022 or 2023 (contingent on UW System initiative regarding course evaluations). | Student Experience 1.3 | Academic Affairs | Metric | Academic Affairs / CITL
| Revive the Inclusive Teaching Fellows program by spring 2022. | Student Experience 1.3 | Academic Affairs | Strategy | Provost |  | 2022-01-01 | 365 | $100,000 for 1/4 release of four scholars
| Program announced by January 2022 for fall implementation | Student Experience 1.3 | Academic Affairs | Metric | Provost
| Upon review of retention and promotion data, make appropriate changes to departmental supports, criteria, and processes related to employment to address equity gaps. | Student Experience 1.3 | Business Affairs | Strategy | Human Resources |  | 2022-01-01 | 730 | Staff time
| Review completed and changes communicated to departments by Dec 2022 | Student Experience 1.3 | Business Affairs | Metric | Human Resources
| Require all search committees to assess candidates’ commitment to EDI. | Student Experience 1.3 | Business Affairs | Strategy | Human Resources |  | 2022-01-01 | 330
| Requirement integrated into search process by Dec 2022 | Student Experience 1.3 | Business Affairs | Metric | Human Resources
| Work with Human Resources to develop a robust best-practice plan to diversify all full-time faculty and staff to better represent the student body population by employing new and novel approaches that realize and retain greater numbers of staff. | Student Experience 1.3 | Business Affairs | Strategy | Human Resources |  | 2022-01-01 | 730 | $6000 for job postings, potential diveristy staff recruiter
| Plan submitted by Dec 2023 | Student Experience 1.3 | Business Affairs | Metric | Human Resources
| We will create an enriched learning environment through the use of advanced evidence-based practices and educational tools, innovative technologies, and equity-minded pedagogies. | Student Experience 1.4 |  | Goal
| Address curricular barriers to student success in their first two years. | Student Experience 1.4 |  | Outcome | Retention Steering Committee |  | 2021-07-01 | 1825
| Develop a proposal for mandatory mid-term grade reporting and present it as a policy to Academic Affairs Committee. | Student Experience 1.4 | Academic Affairs | Strategy | Retention Steering Committee | In Progress | 2021-09-01 | 330
| Proposal submitted by May 2022 | Student Experience 1.4 | Academic Affairs | Metric | Retention Steering Committee
| Address administrative barriers to student success in the first two years. | Student Experience 1.4 |  | Outcome | Retention Steering Committee |  | 2021-07-01 | 1825
| Conduct an audit on holds that inhibit registration to determine their necessity and impact. | Student Experience 1.4 | Academic Affairs | Strategy | Retention Steering Committee |  | 2022-01-01 | 120
| Report submitted by May 2022 | Student Experience 1.4 | Academic Affairs | Metric | Retention Steering Committee
| Develop a core set of intentional learning outcomes and programs to promote student development within Student Affairs programs and services. | Student Experience 1.4 | Student Affairs | Outcome | SAAT / SA Departmental Directors |  | 2021-07-01 | 365
| Create, promote, and emphasize the use of Student Affairs learning outcomes into all co-curricular programming | Student Experience 1.4 | Student Affairs | Strategy | SAAT / SA Departmental Directors | In Progress | 2021-07-01 | 365 | Staff Time
| Learning outcomes are integrated by May 2022 | Student Experience 1.4 | Student Affairs | Metric | SAAT / SA Departmental Directors |  |  |  | Staff Time
| Create, promote, and emphasize the use of Student Affairs programs outcomes into all co-curricular planning | Student Experience 1.4 | Student Affairs | Strategy | SAAT / SA Departmental Directors | In Progress | 2021-07-01 | 365 | Staff Time
| Programming outcomes are integrated by May 2022 | Student Experience 1.4 | Student Affairs | Metric | SAAT / SA Departmental Directors |  |  |  | Staff Time

## PMP Goal Organization
Purpose Made Possible Goals
We will align University expenditure levels with available resources. Annual expenditure levels in university departments will be within the annual state budget allocation or the program revenue generated. | Finance 1.1
We will utilize financial models that will be data informed, transparent, objective, and action oriented. The financial models will inform decisions to allocate and reallocate resources. | Finance 1.2
We will create ethical processes and metrics to support the financial models and to inform decision-making, resulting in greater transparency and understanding of the current financial situation of the university, the rationale for decision making, and the need to ensure long-term financial sustainability. | Finance 1.3
We will encourage and achieve financial growth. New revenue sources will be explored and analyzed for financial viability. These new revenue sources will complement existing financial resources to allow diversification of university finances. | Finance 1.4
We will increase and expand access by enhancing strategic partnerships with high schools and other educational institutions that support college-bound student success, college completion, and enrollment growth for a diverse student body. | Student Success 1.1
We will grow programs and harness technologies to support post-traditional and graduate learners through creative delivery methods including but not limited to branch campuses, hybrid, online, or collaborative models. This shall involve strengthening student support in terms of course timing/availability, academic calendars, evening/weekend classroom, office and service access, and prior learning experience. | Student Success 1.2
We will develop and implement internal systems and structures to better serve diverse prospective students in our market. The system should use data to determine financial and program viability, and inform new programs/offerings relevant to K-12 traditional, post-traditional, graduate, and continuing ed students. | Student Success 1.3
We will increase our unique cross-disciplinary work to leverage (or promote) our strengths in sustainability, global awareness, and diversity, equity, and inclusion, for prospective students at all credential and continuing education levels. | Student Success 1.4
We will prioritize and expand high-impact practices (HIP) to boost student learning, development, and engagement. | Student Experience 1.1
We will deliver vibrant yet tailored student services that support the retention and success of all students. | Student Experience 1.2
We will build and enhance a community that values inclusion, equity, and diversity. | Student Experience 1.3
We will create an enriched learning environment through the use of advanced evidence-based practices and educational tools, innovative technologies, and equity-minded pedagogies. | Student Experience 1.4
We will collaborate both internally and with community members and organizations to create initiatives that support economic and community development. We will share our stories with each other and our stakeholders and work together to enhance our community. | Communities 1.1
In our internal and external collaborations we will focus on our commitment to be more inclusive and promote equity and diversity. | Communities 1.2
As an educational and cultural resource for the communities we serve, we will develop and promote new types of collaborations that align with the mission of UW-Stevens Point and that lead to greater efficiency, greater opportunity for a UWSP credential, and greater student success through internships and other experiential learning. | Communities 1.3

## Sheet1 (hidden)
FY22 | Executive
FY23 | Advancement
FY24 | Marketing & Enrollment
FY25 | Student Affairs
FY26 | Business Affairs
Academic Affairs